## Slide 1: Tellvoice Project Roadmap for ACC ACCTSR / ACC-SMM
Tellvoice Technology
7 Jan 2016
Rev 3.0 / 06JAN2016

## Slide 2: Agenda
Overall Project Roadmap 2015-2016
ACC-SMM Roadmap 2015-2016

## Slide 3: ACC-SMM Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
SMM Corporate E-Mail and Web Chat | 
Phase 1 Interim solution with separated domain Partial features for corporate e-mail | 
Phase 2 Complete solution within single SMM platform Complete enhanced corporate e-mail features | 
PANTIP New Web Service | 
New PANTIP API implementation in SMM Include 12-month service fee for Pantip | 
Social Analytic | 
Integrate to TV survey platform Sentimental analysis of AIS customers Sentimental analysis of competitors Identify customer intention, sentiment Comparison of 2 products/services Cloud keyword tag | 
Phase 2
Full Solution
Phase 1
Interim Solution
Ph 1 – 15DEC
SMM Corporate E-Mail and Web Chat
Ph 2 – 31MAR
Currently
On-going Project
Survey Platform Integration
Prod – 25NOV
SMM Survey Platform
Prod – 29JUL
Social Other Sites
Social Other Sites
Pantip New WS Development
Integration w/SMM
Social Analytic
S-Sense Integration
Analytical Tools
Ph 2 – 27MAY
Social Analytic
Platform
Ph 1 – 31MAR
INFRASTRUCTURE
IMPLEMENTATION PLAN
SERVICE ROLL-OUT PLAN
Social Analytic
Ph 2 – 27MAY
Ph 1 – 31MAR
Social
Other Sites
Prod – 29JUL
Ph 1 – 15DEC
(Completed)
SMM Corporate
E-Mail and
Web Chat
Ph 2 – 29APR
Auto Survey
Prod – 26FEB
Facebook Myanmar
Prod – 26FEB
SMM Agent
Quality
Assurance
Prod – 29JUL
Prod – 29JUL
SMM Agent Quality Assurance
SMM Agent QA
Provide information for QA
To improve operation efficiency
SMM Survey Platform
Prod – 25NOV

## Slide 4: Update ACC SMM
LINE and LINE@ accounts
Auto Survey
Facebook Myanmar
Pantip and Social Other Sites
Social Analytic—Q1/2016
QA Analysis
Integration with Other AIS Systems
  Workforce management
  Siebel
  SFF
  SuperScreen

## Slide 5: LINE and LINE@
Summary of features on Social Analytic Platform
Business—impact and benefits / Cost / Technical
Benefits
Most popular messaging platform in Thailand
Handling each customer individually
Group messaging

## Slide 6: Auto Survey Facebook Myanmar
Auto Survey
Integration with AIS Survey system
Additional development for system integration
Facebook Myanmar
Supported on UNICODE encoding
Additional development on Zaw Gyi character encoding support

## Slide 7: Pantip and Social Other Sites
Pantip New Web Service
Include 12-month service fee 33,000 Baht/month
Kapook / Manager
Already contact and able to provide information.
To be discussed about cost and technical information.
Sanook / M-Thai
Sanook—Not open publicly. Request to handle case-by-case only.
M-Thai—No policy to provide information.

## Slide 8: Social Analytic Platform (1)
Summary of features on Social Analytic Platform
Sentimental analysis of AIS customers
Sentimental analysis of competitors
Identify customer intentions and sentiments
Comparison of 2 products/services
Cloud keyword tag
Customized Analysis Reports using BI Tool

## Slide 9: Social Analytic Platform (2)
Summary new features on Sentimental Analysis Engine (S-Sense) V.2
สามารถวิเคราะห์ความคิดเห็นจากข้อความ (Sentiment) เชิงบวก (Positive) / เชิงลบ (Negative)
สามารถวิเคราะห์จุดประสงค์ของผู้เขียน (Intention) ประกาศและโฆษณา / ร้องขอ / คำถาม / แสดงความคิดเห็น
สามารถวิเคราะห์ข้อความเชิงเปรียบเทียบระหว่างชื่อสินค้า/บริการ 2 ชื่อ พร้อมทั้งระบุมุมมองที่เปรียบเทียบ ประโยคความคิดเห็น: “call center สินค้า A บริการดีกว่า call center สินค้า B” โดยระบบจะวิเคราะห์ผลว่า สินค้า A ได้รับความคิดเห็นเชิงบวก ในขณะที่ สินค้า B ได้รับความคิดเห็นเชิงลบในเรื่องของการให้บริการ เป็นต้น

## Slide 10: Social Analytic Platform (3)
Summary new features on Sentimental Analysis Engine (S-Sense) V.2
สามารถวิเคราะห์ความเชื่อมโยงของชื่อสินค้ากับความคิดเห็นเชิงบวกลบ ประโยคความคิดเห็น “สินค้า A หน้าจอคมชัดและสีสันสดใส” ระบบจะวิเคราะห์ผลว่า “สินค้า A ได้รับความคิดเห็นเชิงบวกในเรื่องคุณสมบัติของหน้าจอ”
สามารถวิเคราะห์โครงสร้างของกริยาวลีได้ การใช้กริยาวลีของคำว่า “อยากใช้” “อยากใช้ สินค้า A จังเลย” “อยากจะกลับไปใช้ สินค้า A อีก” ซึ่งระบบสามารถให้ผลการวิเคราะห์ใช้กริยาวลีดังกล่าวเป็นเชิงบวกเหมือนกัน ทั้งในกรณีคำกริยาที่อยู่ติดกันหรือแยกจากกันได้

## Slide 11: Social Analytic Platform (4)
Summary new features on Sentimental Analysis Engine (S-Sense) V.2
สามารถวิเคราะห์คำกำหนดทิศทางที่มีผลต่อความเห็นได้ เช่น คำว่า “ลดลง” “เพิ่มขึ้น” “น้อยกว่า” เป็นต้น “รถยนต์ยี่ห้อ A กินน้ำมันน้อยกว่ายี่ห้ออื่น” “สินค้า B มีความจุของแบต ลดลงกว่ารุ่นก่อน” ซึ่งระบบสามารถวิเคราะห์ผลในประโยคแรกได้ว่า ยี่ห้อ A ได้รับผลเชิงบวกในเรื่องการ “กินน้ำมัน” และวิเคราะห์ผลในประโยคที่สองได้ว่า สินค้า B ได้รับผลเชิงลบในเรื่อง “ความจุของแบต”

## Slide 12: SMM Agent Quality Assurance
To provide information about Agent for QA.
Detailed analysis of each agent
Random pick-up cases for analysis
Compute handling time
For improving operational efficiency
Customized Analysis Reports using BI Tool

## Slide 13: SMM Survey Platform
Summary of features on Social Analytic Platform
Sentimental analysis of AIS customers
Sentimental analysis of competitors
Identify customer intentions and sentiments
Comparison of 2 products/services
Cloud keyword tag
Customized Analysis Reports using BI Tool

## Slide 14: Survey Statistical Report by Agent

## Slide 15: Update ACC SMM
LINE and LINE@ accounts
Facebook Myanmar
Social Other Sites
Auto Survey
Pantip
Social Analytic—Q1/2016
QA Analysis
Integration with Other AIS Systems
Requests from MD-ACC

## Slide 16: Requests from MD-ACC
Requests (Web Chat) | Solutions Review | Duration
ปุ่ม extend time (ต่อเวลาครั้งละ 5 นาที) โดยปุ่มอยู่ฝั่ง agent | สามารถดำเนินการแก้ไขเพิ่มเติมได้ | 2 สัปดาห์ นับจากได้รับ CR
Auto message ของแต่ละ ปัญหา | ต้องการรายละเอียดความต้องการเพิ่มเติม | 
Enhance ต่อสายให้คุยกับ agent ได้เลย (ต้องไปคุยเรื่อง interface กับทีมไหนเพิ่มเติม) | ต้องการรายละเอียดความต้องการเพิ่มเติม หารือกับทีมคุณพิเชษฐ์ เพื่อขอข้อมูล Solution เพิ่มเติม | 
Self service ในมุมของ auto message คล้ายๆ ask aunjai | ต้องการรายละเอียดความต้องการเพิ่มเติม นัดหารือกับทีมงาน Ask Aunjai | 

## Slide 17: Thank you

## Slide 18: END OF SLIDE

## Slide 19: Overall Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
Engagement Survey
Ph 2 – 30NOV
Ph 1 - 27OCT
Currently On-going Project
Phase 1-2 Cost – 1 M Baht
Customer Track & Trace
Phase 3
Customer Track & Trace
Ph 2 – 15DEC
Ph 1 - 19OCT
Currently On-going Project
Started in SEP’2015
Phase 1-2 Cost
1.5 M Baht
Phase 2
Full Solution
Phase 1
Interim Solution
Ph 1 – 30NOV
SMM Corporate E-Mail and Web Chat
Ph 2 – 31MAR
Currently On-going Project
Phase 1-2 Cost
2 M Baht
Survey Platform Integration
Prod – 31AUG
TV SimplySurvey Platform Integration
* Included with Phase 2
TV Survey Platform
Phase 2
Integration IVR Outbound
Integration ACC-SMM
Survey Analytic Report
Phase 1
New Survey Engine
Multiple Channels
Reporting
Ph 1 – 31JUL
TV SimplySurvey Platform
Ph 2 – 31OCT
Phase 1-2 Cost – 8.2 M Baht
Phase 2
TV SimplyOutbound
New Framework
Full Capacity Expansion
Phase 1
New 120 Ports
Ph 1 – 26FEB
IVR Outbound Capacity Expansion
Ph 2 – 31MAY
Phase 1-2 Cost
7.2M Baht
Prod – 29APR
PANTIP New
Web Service
Cost – 1.4 M Baht
PANTIP New Web Service
New WS Development
Integration w/SMM
Social Analytic
S-Sense Integration
Analytical Tools
Prod – 30NOV
Social Analytic
Cost – 4 M Baht
Prod – 29APR
Web Board
Channels
Web Board Channels
Manager / Kapook
Cost – TBD

## Slide 20: ATSR Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
Engagement Survey
Ph 2 – 30NOV
Ph 1 - 27OCT
Currently On-going Project
Customer Track & Trace
Phase 3
Customer Track & Trace
Ph 2 – 15DEC
Ph 1 - 19OCT
Currently On-going Project
Started in SEP’2015
Phase 1-2 Cost
1.5M Baht
Phase 2
Phase 1
Ph 1 – 31JUL
TV SimplySurvey Platform
Ph 2 – 31OCT
Phase 1-2 Cost – 8.2M Baht
Phase 2
Phase 1
Ph 1 – 26FEB
IVR Outbound Capacity Expansion
Ph 2 – 31MAY
Phase 1 Cost
1.9M Baht
Phase 2 Cost
5.3M Baht
Phase 1-2 Cost
1M Baht
Customer Track & Trace | 2.5 M Baht
Phase 1—Trouble Ticket (TT) Go-Live 19OCT Phase 2—Service Request (SR) Go-Live 15DEC Phase 3—Device Repair Tracking (Phase 1-2 = 1.5M / Phase 3 = 1 M Baht) | 
Engagement Survey | 1 M Baht
Enhanced ATSR Outbound Survey Features Complex condition question and answer Category of customer’s response | 
IVR Outbound Capacity Expansion |  | 7.2 M Baht
Phase 1 New additional 120 ports (4 E1) with new server Interim solution using exist. IVR | Phase 2 New servers expansion New system architecture support additional capacity New framework to support TV SimplySurvey platform Enhanced features Reporting tools for TV SimplyOutbound | 
TV SimplySurvey Platform |  | 8.2 M Baht
Phase 1 TV Simply survey engine Survey template design Survey to various channels—IVR, Web, SMS, e-mail, Social channels (FB/TW) Survey analysis Reporting tools for survey Sentimental analysis | Phase 2 Integrate with ATSR Outbound new framework Integrate with NICE recording to trace back to customer and agent conversation | 

## Slide 21: ACC-SMM Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
SMM Corporate E-Mail and Web Chat | 2 M Baht
Phase 1 Interim solution with separated domain Partial features for corporate e-mail | 
Phase 2 Complete solution within single SMM platform Complete enhanced corporate e-mail features | 
PANTIP New Web Service | 1.4 M Baht
New PANTIP API implementation in SMM Include 12-month service fee for Pantip | 
TV SimplySurvey Platform Integration | 
Phase 2 of TV SImplySurvey Platform Integration with SMM with TV SimplySurvey Platform Cost included with the other project | 
Social Analytic | 4 M Baht
Integrate to TV survey platform Sentimental analysis of AIS customers Sentimental analysis of competitors Identify customer intention, sentiment Comparison of 2 products/services Cloud keyword tag | 
Phase 2
Full Solution
Phase 1
Interim Solution
Ph 1 – 30NOV
SMM Corporate E-Mail and Web Chat
Ph 2 – 31MAR
Currently On-going Project
Phase 1-2 Cost
2 M Baht
Survey Platform Integration
Prod – 31AUG
TV SimplySurvey Platform Integration
* Included with Phase 2
TV Survey Platform
Prod – 29APR
PANTIP New
Web Service
Cost – 1.4 M Baht
PANTIP New Web Service
New WS Development
Integration w/SMM
Social Analytic
S-Sense Integration
Analytical Tools
Prod – 30NOV
Social Analytic
Cost – 4 M Baht
Prod – 29APR
Web Board
Channels
Web Board Channels
Manager / Kapook
Cost – TBD

## Slide 22: Summary Projects 2015-2016
No | Project | Cost | Target | Status
1 | (CR) ATSR ACC Contact Analytic |  | 31 May 2015 | Completed on Prod.
2 | (CR) ATSR ACC Privilege Loyalty Survey |  | 22 Oct 2015 | Completed on Prod.
3 | ACC Customer Track & Trace | 2.5 M |  | 
 | 3.1 Phase 1—TT | 1.5 M | 19 Oct 2015 | Completed on Prod.
 | 3.2 Phase 2—SR |  | 15 Dec 2015 | Completed on Prod.
 | 3.3 Phase 3—Device Repair Tracking | 1 M | 31 Mar 2015 | (Tentative)
4 | ATSR ACC Engagement Survey | 1 M |  | 
 | 4.1 Phase 1 |  | 27 Oct 2015 | Completed on Prod.
 | 4.2 Phase 2 |  | 29 Jan 2016 | Ongoing Development
5 | IVR Outbound Capacity Expansion | 7.2 M |  | 
 | 5.1 Phase 1 | 1.9 M | 28 Feb 2016 | * Subject to approval
 | 5.2 Phase 2 | 5.3 M | 31 May 2016 | (Tentative)
6 | TV SimplySocial Platform | 8.2 M |  | 
 | 6.1 Phase 1 | 4.7 M | 31 Jul 2016 | (Tentative)
 | 6.2 Phase 2 | 3.5 M | 31 Oct 2016 | (Tentative)

## Slide 23: Summary ACC-SMM Projects
No | Project | Cost | Target | Status
1 | SMM Corporate E-Mail and Web Chat | 2 M |  | 
 | 1.1 Phase 1 Interim Solutions |  | 30 Nov 2015 | Ongoing Development
 | 1.2 Phase 2 |  | 31 Mar 2016 | (Tentative)
2 | PANTIP New Web Service | 1.4 M | 31 Mar 2016 | (Tentative)
3 | Survey Platform Integration |  | 31 Aug 2016 | (Tentative)
4 | Social Analytic | 4 M | 30 Nov 2016 | (Tentative)

## Slide 24: ATSR Outbound Existing Architecture
Current Capacity 10 E1 (300 ports)
IVR1 = 6 E1 (180)
IVR2 = 4 E1 (120)
Daily capacity at 9,000 calls/hour or at 90,000 calls/day at 10 peak-hours/day

## Slide 25: IVR Outbound New Architecture
Current Capacity 14 E1 (420 ports)
IVR1 = 6 E1 (180) / IVR2 = 4 E1 (120)
IVR3 = 4 E1 (120) – NEW
Daily capacity at 12,600 calls/hour or at 126,000 calls/day at 10 peak-hours/day

## Slide 26: ATSR Outbound Enhancement
10 Types
Lists
Siebel
PDS
QIS
Qmatic
Manual
AIS Shop
Telewiz
Web
Facebook
Twitter
Pantip
E-Mail
Web Chat
Web Board
ATSR Outbound System
List
Management
Call Management
Survey
Management
Reporting
IVR
Systems
Agents
Customers
Existing ATSR Outbound System
SMS GW
10 Types
Lists
Siebel
PDS
QIS
Qmatic
Manual
AIS Shop
Telewiz
ATSR Outbound System
List
Management
Call Management
Survey
Engine
IVR
Systems
Agents
Customers
New ATSR Outbound System Enhancement
SMS GW
Analysis and Reporting
Sentimental Analysis Engine
Speech-to-
Text Engine
ACC Social Media Monitoring System (ACC-SMM)

## Slide 27: END OF SLIDE

## Slide 28: ATSR Outbound Enhancement Feature
Capacity expansion
Survey engine
Survey to various channels—IVR, Web, SMS, e-Mail, Social Channels (FB/TW)
Survey analysis
Reporting
Sentimental Analysis
Speech-to-Text Transcription

## Slide 29: ATSR Outbound Enhancement Product
No. | Feature | Product
1 | Survey engine | Tellvoice customize
2 | Survey analysis | Tellvoice customize
3 | Reporting | Jaspersoft
4 | Sentimental Analysis | NECTEC S-Sense
5 | Speech-to-Text Transcription | NECTEC PARTY

## Slide 30: ATSR Outbound Functionalities List Management
Imported File List
Filter Rule
Import File Action

## Slide 31: Imported File List

## Slide 32: Filter Rule

## Slide 33: Imported File Action

## Slide 34: ATSR Outbound Job Management

## Slide 35: Survey Question Setting

## Slide 36: Survey Validity Period

## Slide 37: IVR Survey Job Overview

## Slide 38: IVR Call History Report

## Slide 39: Survey Statistical Report by Agent

## Slide 40: Survey Summary Result

## Slide 41: Solutions for ATSR Outbound Enhancement
Enhanced feature on existing ATSR Outbound system
Capacity expansion
Survey engine
Survey to various channels—IVR, Web, SMS, e-Mail, Social Channels (FB/TW)
Survey analysis
Reporting
Sentimental Analysis
Speech-to-Text Transcription

## Slide 42: ATSR Outbound Enhancement
10 Types
Lists
Siebel
PDS
QIS
Qmatic
Manual
AIS Shop
Telewiz
Web
Facebook
Twitter
Pantip
E-Mail
Web Chat
Web Board
ATSR Outbound System
List
Management
Call Management
Survey
Management
Reporting
IVR
Systems
Agents
Customers
Existing ATSR Outbound System
SMS GW
10 Types
Lists
Siebel
PDS
QIS
Qmatic
Manual
AIS Shop
Telewiz
ATSR Outbound System
List
Management
Call Management
Survey
Engine
IVR
Systems
Agents
Customers
New ATSR Outbound System Enhancement
SMS GW
Analysis and Reporting
Sentimental Analysis Engine
Speech-to-
Text Engine
ACC Social Media Monitoring System (ACC-SMM)

## Slide 43: ATSR Outbound Plan
M1 |  | M2 |  | M3 |  | M4 |  | M5 |  | M6 |  | M7 |  | M8 |  | M9 |  | M10 | 
Jul 15 |  | Aug 15 |  | Sep 15 |  | Oct 15 |  | Nov 15 |  | Dec 15 |  | Jan 16 |  | Feb 16 |  | Mar 16 |  | Apr 16 | 
Interactive Survey Questions
Phase 1
Phase 2
  Phase 1 Interactive Survey Questions
  Application enhancement to support interactive survey questions design
  Phase 2 Key Outcomes & Scope
Capacity expansion
Survey engine
Survey to various channels—IVR, Web, SMS, e-Mail, Social Channels (FB/TW)
Survey analysis
Reporting
Sentimental Analysis
Speech-to-Text Transcription
Phase 2 – Enhancement Features
Prod. Deploy 28/9
Prod. Deploy
29/1
Prod. Deploy
25/3
Phase 2
Capacity Expansion
Prod. Deploy
30/10

## Slide 44: ATSR Projects
Projects | Planned Target
Engagement Survey | SEP 2015 – NOV 2015 Phase 1 Deployment 27 OCT Phase 2 Deployment 15 NOV
ATSR Outbound Capacity Expansion | * Proposed by Tellvoice
New ATSR Outbound Survey Framework | * May be combined with Item 4
New Survey Platform Multiple Channels—Voice, SMS, e-Mail, Web Chat, Facebook Reporting—Dashboard and Reports Integrate with NICE recording for reference back to recorded session | 
Personal Survey/Greeting | Integration with TTS platform
Customer Effort Score | Q1—MAR 2016
Customer Analytic (Speech Analytic) | 

## Slide 45: ATSR Projects
Complete loop—when customer responds to survey with low score, the system alerts and reference back to the voice recording of that call sessions for evaluate. Then call back to customer within 3 hours.
Speech-to-Text engine
Emotion detection

## Slide 46: END OF SLIDE

## Slide 47: ATSR Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
Engagement Survey
Ph 2 – 15NOV
Ph 1 - 27OCT
Currently On-going Project
Customer Track & Trace
Phase 3
Customer Track & Trace
Ph 2 – 15DEC
Ph 1 - 19OCT
Currently On-going Project
Started in SEP’2015
Phase 1-2 Cost
1.5M Baht
Phase 2
Phase 1
Ph 1 – 31JUL
TV SimplySurvey Platform
Ph 2 – 31OCT
Phase 1-2 Cost – 12M Baht
Phase 2
Phase 1
Ph 1 – 15DEC
IVR Outbound Capacity Expansion
Ph 2 – 31MAR
Phase 1-2 Cost
6M Baht
Phase 1-2 Cost
1M Baht
Customer Track & Trace | 1.5 M Baht
Phase 1—Trouble Ticket (TT) Go-Live 19OCT Phase 2—Service Request (SR) Go-Live 15DEC Phase 3—Device Repair Tracking | 
Engagement Survey | 1 M Baht
Enhanced ATSR Outbound Survey Features Complex condition question and answer Category of customer’s response | 
IVR Outbound Capacity Expansion | 6 M Baht
Phase 1 New additional 120 ports (4 E1) with new hardware Phase 2 VM server relocation / VM server expansion New framework to support TV SimplySurvey platform Enhanced features Reporting tools for TV SimplyOutbound | 
TV SimplySurvey Platform |  | 12 M Baht
Phase 1 TV Simply survey engine Survey template design Survey to various channels—IVR, Web, SMS, e-mail, Social channels (FB/TW) Survey analysis Reporting tools for survey Sentimental analysis | Phase 2 Integrate with ATSR Outbound new framework Integrate with NICE recording to trace back to customer and agent conversation | 

## Slide 48: ATSR Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
Engagement Survey
Ph 2 – 15NOV
Ph 1 - 27OCT
Currently On-going Project
Customer Track & Trace
Phase 3
Customer Track & Trace
Ph 2 – 15DEC
Ph 1 - 19OCT
Currently On-going Project
Started in SEP’2015
Phase 1-2 Cost
1.5M Baht
Phase 2
Phase 1
Ph 1 – 31JUL
TV SimplySurvey Platform
Ph 2 – 31OCT
Phase 1-2 Cost – 12M Baht
Phase 2
Phase 1
Ph 1 – 15DEC
IVR Outbound Capacity Expansion
Ph 2 – 31MAR
Phase 1-2 Cost
6M Baht
Phase 1-2 Cost
1M Baht
Customer Track & Trace | 1.5 M Baht
Phase 1—Trouble Ticket (TT) Go-Live 19OCT Phase 2—Service Request (SR) Go-Live 15DEC Phase 3—Device Repair Tracking | 
Engagement Survey | 1 M Baht
Enhanced ATSR Outbound Survey Features Complex condition question and answer Category of customer’s response | 
IVR Outbound Capacity Expansion | 6 M Baht
Phase 1 New additional 120 ports (4 E1) with new hardware Phase 2 VM server relocation / VM server expansion New framework to support TV SimplySurvey platform Enhanced features Reporting tools for TV SimplyOutbound | 
TV SimplySurvey Platform |  | 12 M Baht
Phase 1 TV Simply survey engine Survey template design Survey to various channels—IVR, Web, SMS, e-mail, Social channels (FB/TW) Survey analysis Reporting tools for survey Sentimental analysis | Phase 2 Integrate with ATSR Outbound new framework Integrate with NICE recording to trace back to customer and agent conversation | 

## Slide 49: Overall Roadmaps 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
Engagement Survey
Ph 2 – 15NOV
Ph 1 - 27OCT
Currently On-going Project
Customer Track & Trace
Phase 3
Customer Track & Trace
Ph 2 – 15DEC
Ph 1 - 19OCT
Currently On-going Project
Started in SEP’2015
Phase 2
Full Solution
Phase 1
Interim Solution
Ph 1 – 24NOV
SMM Corporate E-Mail
Ph 2 – 31MAR
Currently On-going Project
Survey Platform Integration
Prod – 31AUG
Survey Platform Integration
* Included with Phase 2
TV Survey Platform
Phase 2
Integration IVR Outbound
Integration ACC-SMM
Survey Analytic Report
Phase 1
New Survey Engine
Multiple Channels
Reporting
Ph 1 – 31JUL
TV Survey Platform
Ph 2 – 31OCT
Phase 2
Full Capacity Expansion
with Enhancement Features
Phase 1
New 120 Ports
Ph 1 – 15DEC
IVR Outbound Capacity Expansion
Ph 2 – 31MAR
PANTIP New Web Service
Commercial Deal
Technical Implementation
Prod – 31MAR
PANTIP New Web Service
Social Analytic
S-Sense Integration
Analytical Tools
Prod – 30NOV
Social Analytic
NO COST

## Slide 50: ATSR Outbound Plan
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
  Phase 1 Interactive Survey Questions
  Application enhancement to support interactive survey questions design
  Phase 2 Key Outcomes & Scope
Capacity expansion
Survey engine
Survey to various channels—IVR, Web, SMS, e-Mail, Social Channels (FB/TW)
Survey analysis
Reporting
Sentimental Analysis
Speech-to-Text Transcription
Phase 2
Enhancement Features
Phase 1
New 120 Ports
Ph 1 – 15DEC
IVR Outbound Capacity Expansion
Ph 2 – 31MAR
Engagement Survey
Ph 2 – 15NOV
Ph 1 - 27OCT
Currently On-going Project
Customer Track & Trace
Phase 3
Customer Track & Trace
Ph 2 – 15DEC
Ph 1 - 19OCT
Currently On-going Project
Started in SEP’2015
Phase 2
Enhancement Features
Phase 1
New 120 Ports
Ph 1 – 15DEC
TV Survey Platform
Ph 2 – 31MAR

## Slide 51: The Big Picture
ACC SOCIAL MEDIA
MONITORING
SURVEY
ENGINE
ATSR
OUTBOUND
FB
TW
CUSTOMER
MOBILE
EMAIL
PANTIP
WEB BOARD
WEB CHAT

## Slide 52: ATSR Outbound Existing Modules
List Management
Call Management
IVR1
IVR2
SMS
Gateway
10 Types
Lists
Siebel
PDS
QIS
Qmatic
Manual
Agents

## Slide 53: ATSR Outbound New Modules
List Management
Call Management
IVR1
IVR2
SMS
Gateway
10 Types
Lists
Siebel
PDS
QIS
Qmatic
Manual
Survey
Engine
Survey Analysis and Reporting
Web
Social Media
E-Mail
Agents
Sentimental
Analysis
Speech-to-Text
Engine

## Slide 54: ACC-SMM Roadmap 2015-2016
2015 |  |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SEP |  | OCT |  | NOV |  | DEC |  | JAN |  | FEB |  | MAR |  | APR |  | MAY |  | JUN |  | JUL |  | AUG |  | SEP |  | OCT |  | NOV |  | DEC | 
Survey Platform Integration
Prod – 31AUG
TV SimplySurvey Platform Integration
* Included with Phase 2
TV Survey Platform
PANTIP New Web Service
Commercial Deal
Technical Implementation
Prod – 31MAR
PANTIP New Web Service
Cost – 1 M Baht
Social Analytic
S-Sense Integration
Analytical Tools
Prod – 30NOV
Social Analytic
Cost – 4M Baht
SMM Corporate E-Mail and Web Chat | 2 M Baht
Phase 1 Interim solution with separated domain Partial features for corporate e-mail | 
Phase 2 Complete solution within single SMM platform Complete enhanced corporate e-mail features | 
PANTIP New Web Service | 1 M Baht
New PANTIP API implementation in SMM | 
TV SimplySurvey Platform Integration | 
Phase 2 of TV SImplySurvey Platform Integration with SMM with TV SimplySurvey Platform Cost included with the other project | 
Social Analytic | 4 M Baht
Integrate to TV survey platform Sentimental analysis of AIS customers Sentimental analysis of competitors Identify customer intention, sentiment Comparison of 2 products/services Cloud keyword tag | 
Phase 2
Full Solution
Phase 1
Interim Solution
Ph 1 – 30NOV
SMM Corporate E-Mail and Web Chat
Ph 2 – 31MAR
Currently On-going Project
Phase 1-2 Cost
2 M Baht